## Combined Efforts
Sr.No | Application Name |  | Combined Efforts | Front-end | Back-end
1 | Web App |  | 294 | 98 | 196
Combined Efforts |  |  | 294 | 98 | 196
| Other Phases | % Attribution
1 | Project management | 5 | 14.7
2 | Business Analysis | 5 | 14.7
3 | Technical Design | 0 | 0
4 | UI Design & Development Support | 5 | 14.7
5 | Documentation | 5 | 14.7
6 | QA Testing | 20 | 58.8
7 | Implementation & Support | 0 | 0
| Total Estimation (Hours) |  | 411.6
8 | 30 day warranty post Go Live | 0 | 0
| Grand Total Estimation (Hours) |  | 411.6
USD Cost / Hour
|  | 18 | 7408.8
| Total Cost (USD) | 20 | 8232

## Feature List - Web App
Cost Estimation and Feature Listing for Hanwha Dashboard Web Application - Phase 4 - ANPR Module
Development + Unit Testing Efforts
| Sr No | Features/Use Case/WBS | Sub - Features/Comments/Implementation | % Attribution | Combined | Front-end | Back-end
Web Application
| 1 | ANPR Module | Change in License App for ANPR Module. |  | 8 | 4 | 4
|  |  | Add ANPR option in manage device when add edit device. Here user will also define Entry / Exit setting for specific camera. |  | 16 | 8 | 8
|  |  | Implementation of capturing ANPR event from camera. |  | 16 | 0 | 16
|  |  | Validating the vehicle event data and open the gate barrier integration alarm by CGI command. Same process for exit vehicle. |  | 16 | 0 | 16
|  |  | For restricted vehicle gate will not open and alarm command to be given. |  | 4 | 0 | 4
|  |  | Store large image and cropped image of ANPR detection at configured location. |  | 4 | 0 | 4
|  |  | LPR Search Result Screen LPR search parameters => Select the floor/zone/devices => Datetime range => License Plate: Plate series,Vehicle number,Country,Region,Colour,Category,Length => Vehicle: Type,Colour,Manufacturer, Model => Owner Information: Owner,Building,Unit |  | 24 | 16 | 8
|  |  | LPR search result in the grid with standard pagination and export to CSV option |  | 52 | 20 | 32
|  |  | In ANPR Configuration, give => Plate Image Storage Location (Configure the path where all the plate images will be store) => Data and image retention period: Configure in the month. After configured retention older image and data will be deleted from the system. Background job will execute daily and delete old data as per retention configuration. (considering delete not archive) |  | 16 | 4 | 12
|  |  | New screen to Register Owners - Name - Building - Unit - email - Allowed vehicle (number of allowed vehicle in parking) - Allowed from time (if it is configured owner cannot enter before this time) - Allowed to time (if it is configured owner cannot enter after this time) - Allowed gates (if it is configured owner can enter on selected gates only) - System Notification for overstay (if vehicle is not exit before Allowed to time) -System notification for 24H stay |  | 32 | 12 | 20
|  |  | New Screen to Register Vehicles - Country - Region - Series - Vehicle number - Registration date - Expired date - Vehicle Owner - RegistrationType[Registered, Visitor, Restricted] - Vehicle Owner (select owner in case if Registered) - Temporary owner name (for Temporary Visitor) - email - Temporary Allowed from time (for Temporary Visitor) - Temporary Allowed to time (for Temporary Visitor) - Temporary Allowed gates (for Temporary Visitor) - System Notification alarm for overstay (if vehicle is not exit before Temporary Allowed to time) - System Notification for 24H stay |  | 16 | 8 | 8
|  |  | Creation of background job for Overstay notification |  | 8 | 0 | 8
|  |  | Creation of background job for 24 Hours Overstay notification |  | 8 | 0 | 8
|  |  | Screen to view audit data, details like who register/update the vehicle/Owner data |  | 32 | 16 | 16
|  |  | CSV upload feature for vehicle registration. |  | 10 | 2 | 8
|  |  | Allow manually open gate barrier from the camera grid. |  | 6 | 2 | 4
|  |  | Set device as maintenance mode On/Off from the grid. Keep open the gate barrier in case of maintenance mode is ON. |  | 6 | 2 | 4
|  |  | Floor/Zone utilization based on In/Out Vehicles. |  | 20 | 4 | 16
|  |  |  | Combined Efforts | 294 | 98 | 196
0

## Out Of Scope
Sr No. | Out Of Scope
1
2

## Assumptions & Queries
Sr No. | Assumptions & Queries
1
2