## Combined Efforts
Sr.No | Application Name |  | Combined Efforts | Front-end | Back-end
1 | Web App |  | 340 | 148 | 192
Combined Efforts |  |  | 340 | 148 | 192
| Other Phases | % Attribution
1 | Project management | 5 | 17
2 | Business Analysis | 5 | 17
3 | Technical Design | 0 | 0
4 | UI Design & Development Support | 5 | 17
5 | Documentation | 5 | 17
6 | QA Testing | 20 | 68
7 | Implementation & Support | 0 | 0
| Total Estimation (Hours) |  | 476
8 | 30 day warranty post Go Live | 0 | 0
| Grand Total Estimation (Hours) |  | 476
USD Cost / Hour
|  | 18 | 8568
| Total Cost (USD) | 20 | 9520

## Feature List - Web App
Cost Estimation and Feature Listing for Hanwha Dashboard Web Application - Phase 4 - Basic Maintenance
Development + Unit Testing Efforts
| Sr No | Features/Use Case/WBS | Sub - Features/Comments/Implementation | % Attribution | Combined | Front-end | Back-end
Web Application
| 13 | Basic Maintenance Features | Change in License App for Maintenance Module. |  | 8 | 4 | 4
|  |  | In Manage Devices, add new fiels in Add/Edit Device - Assets Tag, Manufacturing Date |  | 4 | 2 | 2
|  |  | New Screen to Create / Update Maintenance Plan and view in grid. - Plan name - Duration - Start date - End date - Devices (multi select)) |  | 40 | 16 | 24
|  |  | Background Service will create new data for future maintenance up to 30 days based on the Maintenance Plan created. |  | 16 | 0 | 16
|  |  | New Page to view Maintenance Schedule. |  | 0 | 0 | 0
|  |  | Maintenance Schedule Page- Filter for search maintenance data, User can search by floor, zone, date and maintenance status. (floor and zone mapping will work as per existing implementation) |  | 8 | 8 | 0
|  |  | Maintenance Schedule Page- Display all the maintenance data in grid with standard pagination as per selected filter. |  | 24 | 8 | 16
|  |  | Maintenance Schedule Page - User can export data in CSV. |  | 8 | 0 | 8
|  |  | Maintenance Schedule Page - User will update status to maintenance In Progress and a live preview image will be captured and stored. |  | 16 | 8 | 8
|  |  | Maintenance Schedule Page - User can compare before and after Image and update status to maintenance Completed if result is satisfactory. |  | 12 | 4 | 8
|  |  | Maintenance Schedule Page - Image comparison in percentage will be shown on screen for before and after maintenance. |  | 48 | 8 | 40
|  |  | Maintenance Schedule Page - User can change status to maintenance Rework if required if user is not satisfied with the maintenance. |  | 4 | 2 | 2
|  |  | Maintenance Schedule Page - Rework status history will display under maintenance popup in a table, so that if multiple times Rework is done, then history can be displayed. |  | 16 | 8 | 8
|  |  | Maintenance Schedule Page - User can manually add new record for maintenance of any device in case of any high priority maintenance need. |  | 12 | 4 | 8
|  |  | Maintenance Mode Widget as per Figma design |  | 24 | 16 | 8
|  |  | Camera Disconnection Tracker Widget as per Figma design |  | 24 | 16 | 8
|  |  | Cameras in Maintenance Widget as per Figma design |  | 24 | 16 | 8
|  |  | Camera Maintenance Status Count Widget as per Figma design |  | 24 | 16 | 8
|  |  | System Notification for due maintenance of camera. |  | 12 | 4 | 8
|  |  | New screen to View/Add/Update RMA for a camera - Create new RMA - User can search RMA data by floor zone date and RMA status (In progress/Completed) - Display RMA data in Grid with standard pagination - User will manually mark a camera as "In RMA" and once the camera is back from RMA, he has to manually update that camera is back from RMA. - RMA Start Date Time and RMA End Date Time fields will be given. |  | 16 | 8 | 8
|  |  |  | Combined Efforts | 340 | 148 | 192
0

## Out Of Scope
Sr No. | Out Of Scope
1
2

## Assumptions & Queries
Sr No. | Assumptions & Queries
1
2