## Combined Efforts
Sr.No | Application Name |  | Combined Efforts | Front-end | Back-end
1 | Web App |  | 160 | 64 | 96
Combined Efforts |  |  | 160 | 64 | 96
| Other Phases | % Attribution
1 | Project management | 5 | 8
2 | Business Analysis | 5 | 8
3 | Technical Design | 0 | 0
4 | UI Design & Development Support | 5 | 8
5 | Documentation | 5 | 8
6 | QA Testing | 20 | 32
7 | Implementation & Support | 0 | 0
| Total Estimation (Hours) |  | 224
8 | 30 day warranty post Go Live | 0 | 0
| Grand Total Estimation (Hours) |  | 224
USD Cost / Hour
|  | 18 | 4032
| Total Cost (USD) | 20 | 4480

## Feature List - Web App
Cost Estimation and Feature Listing for Hanwha Dashboard Web Application - Phase 4 - SSM Dashboard
Development + Unit Testing Efforts
| Sr No | Features/Use Case/WBS | Sub - Features/Comments/Implementation | % Attribution | Combined | Front-end | Back-end
Web Application
| 5 | SSM Dashboard in Vision Insight | New Screen to List/Add/Edit Site |  | 16 | 8 | 8
|  |  | Role Permission based Access |  | 8 | 4 | 4
|  |  | Background job will store the data from SSM servers periodically |  | 24 |  | 24
|  |  | New Dashboard to display SSM Widgets |  | 16 | 16
|  |  | Filters for the Dashboard will be 1. SSM Site selection, 2. Datetime selection |  | 4 | 4
|  |  | Below data will be displayed on Dashboard based on selected filter: 1. Total camera count 2. Total SSM Server count 3. Failure camera count 4. Failure SSM server 5. Display server-based data |  | 40 | 16 | 24
|  |  | On clicking on Server-Based Data, below details will be displayed: Server connection details Server storage details per drive Connected / Disconnected devices CPU > system manager, media server RAM > system manager, media server |  | 36 | 16 | 20
|  |  | Health Report - CSV will be downloaded. System will generate CSV report for the selected filter. Report will display each record when device is online/offline. If any device online/offline multiple time within specific period in this case display each record with specific datetime |  | 16 |  | 16
|  |  |  | Combined Efforts | 160 | 64 | 96
0

## Out Of Scope
Sr No. | Out Of Scope
1
2

## Assumptions & Queries
Sr No. | Assumptions & Queries
1
2