## Combined Efforts
Sr.No | Application Name |  | Combined Efforts | Front-end | Back-end
1 | Web App |  | 156 | 80 | 76
Combined Efforts |  |  | 156 | 80 | 76
| Other Phases | % Attribution
1 | Project management | 5 | 7.8
2 | Business Analysis | 5 | 7.8
3 | Technical Design | 0 | 0
4 | UI Design & Development Support | 5 | 7.8
5 | Documentation | 5 | 7.8
6 | QA Testing | 20 | 31.2
7 | Implementation & Support | 0 | 0
| Total Estimation (Hours) |  | 218.4
8 | 30 day warranty post Go Live | 0 | 0
| Grand Total Estimation (Hours) |  | 218.4
USD Cost / Hour
|  | 18 | 3931.2
| Total Cost (USD) | 20 | 4368

## Feature List - Web App
Cost Estimation and Feature Listing for Hanwha Dashboard Web Application - Phase 4 - iDRAC Integration
Development + Unit Testing Efforts
| Sr No | Features/Use Case/WBS | Sub - Features/Comments/Implementation | % Attribution | Combined | Front-end | Back-end
Web Application
| 1 | iDRAC Integration | Separate Menu for iDRAC, with menu options of Configuration Settings and Dashboard |  | 4 | 4 | 0
|  |  | Role Permission based access for iDRAC menu. |  | 8 | 4 | 4
|  |  | New screen to add Dell server with ip, UserName, Password |  | 48 | 24 | 24
|  |  | Event System Notification Criteria creation when Fan, Storage, RAM, Temperature goes beyond the set limit |  | 40 | 16 | 24
|  |  | Live Dashboard (Monitoring View) to see CPU, memory, Storage, Temperature on screen for the selected server |  | 56 | 32 | 24
|  |  |  | Combined Efforts | 156 | 80 | 76
0

## Out Of Scope
Sr No. | Out Of Scope
1
2

## Assumptions & Queries
Sr No. | Assumptions & Queries
1
2