## Combined Efforts
Sr.No | Application Name |  | Combined Efforts | Front-end | Back-end
1 | POS Web App |  | 1760 | 1760 | 0
1 | Consumer Mobile App |  | 236 | 236 | 0
|  |  | 0 | 0 | 0
Combined Efforts |  |  | 1996 | 1996 | 0
| Other Phases | % Attribution
1 | Project management | 4 | 79.84
2 | Business Analysis | 8 | 159.68
3 | Technical Design( Web+ Mobile) | 1 | 19.96
4 | UI Design & Development Support | 8 | 159.68
5 | Documentation | 0 | 0
6 | QA Testing | 15 | 299.4
7 | Implementation & Support- WEB | 1 | 19.96
8 | Implementation & Support- Mobile | 0.5 | 9.98
| Total Estimation (Hours) |  | 2744.5
8 | 30 day warranty post Go Live | 0 | 0
| Grand Total Estimation (Hours) |  | 2744.5
USD Cost / Hour
| Total Cost (USD) | 20 | 54890

## Feature Listing
Cost Estimation & Feature Listing for Phase - 2 Development in Hanwha BI Dashboard Web Application
|  |  |  | Development + Unit testing |  |  | Comment/Query
| Sr No | Main - Features | Sub - Features | Combined | Front-end | Back-end
BI Dashboard Web Application
|  | Collect the data from camera if camera disconnected from application, | Collect the data from camera if camera disconnected from application, during disconnection time data should fetch to the app. Once the camera is connected back, the API will be called and the data is to be ingested for the time when the camera was not connected/offline.
|  | Floor plan widget: Solve UI issue of multiple camera count data overlapping if placed nearby | In floor plan widget, if the camera are nearby, then the count is overlapping and it is difficult to view the count of the camera. As a solution, show the count on hover/selection of camera. On hover/selection, display the count on top of other camera.
|  | Floor plan to stretch the MAP | Allow user to move the map across the screen with zoom in and zoom out also increase the dot size for camera focal rotation. Give option to view floor plan and map in full screen.
Database Limit setting - Retention period, archive option should available.
|  | Database configured on separate server machine | Currently, the database is installed on the same server where the application is installed. Now, give option to install database in separate drive of same server or separate server, connected via LAN and connect the database from that server in the application. In the application installer file, give option to select separate database server location.
|  | Database Auto Backup | Auto back up of database should be done at a specific time of day. Give option in General Configuration Setting to enter the location of separate server where the backup file of database will be stored. Keep backup files of last 7 days and delete old backup files.
|  | Audit Log | Provide feature/screen to view audit log of the application. Provide feature to send log details as email to technical team.
|  | Occupancy - Average occupancy rate | UI modifications in Capacity Utilization Widget. If the utilization is more than the defined capacity, show in red color backgroud or give some blinking effect.
|  | New Widget for API Working/Not Working Camera | Develop a new widget that displays the count of cameras which has API working/ not working.
|  | Selection of API type while adding camera | In Manage Devices, when a camera is added, give option to select the type of API supported by the camera. Because, new cameras of old series are supporting different type of APIs.
|  | Time Format selection | The time format selection in the General Configuration Setting should be applied throughout the application, even in the reports. The time format change should reflect on the screen without manual refreshing of the screen.
|  | Multichannel Camera | In Manage Device screen, add new type of "Multichannel" camera. Give textbox to enter the number of channels supported by the camera. Usually it will be between 2 to 5 channels. Multichannel camera will have separate APIs, details of which will be provided by Bala.
|  | Collabsible Menu (UI improvement) | Left side menu should be collapsible so as to have full utilization of the screen.
|  | Multi-lingual support | Make the application multi-lingual with below mentioned languages supported: Arabic Korean French Mandarin (Chinese) German Spanish Italian Danish (Denmark) Russian
|  | Mobile Responsiveness | The application should be mobile responsive, supporting on tablet/iPad/mobile.
|  | UI Themes | Give option to view the application in 8 more themes.
|  | People In/Out Report | In the People In/Out report, show the difference of In/Out hourly, not showing it as adding up total every hour.
|  | Report Changes | In the Report filter, give custom option to user to select Start Date and End Date. In the Result, give custom option to user to select the time gap for which the report needs to be shown, like 5 Min, 10 Min, 15 Min, 30 Min, 1 Hr, 2 Hr., etc.
|  | Generative AI | Implementation of Generative AI in the application.
|  | People In/Out Report Modification | While exporting the In/Out report to PDF, both In and Out should be shown. Currently it is only showing either In or Out, based on what is visible on the screen.
|  | Widgets design modification | Few widgets are looking similar. Identify and propose different design for these widgets.
|  | Widget Resize | Give option to resize the widget. Also, give option to view the widgets in full screen view.
|  | ANPR API Integration | Automatic Number Plate Recognition Number plate field list to be obtained by calling the API. Bala to provide the API. Add new widget in traffic showing parking slots are Available or Not Available. If Parking Slots are full, show Parking full. Add Parking slots field in Zone creation.
|  | SSM Dashboard in Vision Insight | SSM Dashboard to be integrated in Vision Insight. API and further details will be given and discussed by Bala.
|  | Manage Devices - Export to Excel | Give export to csv feature in Manage Devices screen.
|  | Failover plan | System failover plan
|  |  | Total combined efforts | 0 | 0 | 0