## Combined Efforts
Sr.No | Application Name |  | Combined Efforts | Front-end | Back-end
1 | Web App |  | 2090 | 990 | 1100
2 | Admin Web App |  | 148 | 64 | 84
Combined Efforts |  |  | 2238 | 1054 | 1184
| Other Phases | % Attribution
1 | Project management | 0 | 0
2 | Business Analysis | 0 | 0
3 | Technical Design | 0 | 0
4 | UI Design & Development Support | 0 | 0
5 | Documentation | 7 | 156.66
6 | QA Testing | 0 | 0
7 | Implementation & Support | 0 | 0
| Total Estimation (Hours) |  | 2394.66
8 | 30 day warranty post Go Live | 0 | 0
| Grand Total Estimation (Hours) |  | 2394.66
USD Cost / Hour
| Total Cost (USD) | 18 | 43103.88
With 2 Resource
|  | BA (SRS) (Single resource only) |  | 4 Week |  | 3.9165
|  | For backend Development |  | 13-14 Weeks |  | 13.75
|  | For Frontend Development |  | 12-13 Weeks |  | 12.375
|  | Overall Development including QA Manual + Automation+ BA |  | 21 Weeks
4.5 Months

## Feature List - Web App
Cost Estimation and Feature Listing for Hanwha Dashboard Web Application - Web App Lead
Development + Unit Testing Efforts
| Sr No | Features/Use Case/WBS | Sub - Features | % Attribution | Combined | Front-end | Back-end
Web Application
| 1 | User Login | Users can log in using their own credentials. |  | 8 | 4 | 4
|  |  | User can reset own password (Forgot password) |  | 8 | 4 | 4
|  |  | Change Password |  | 8 | 4 | 4
0
| 2 | User Management | Add/Update/Delete users |  | 28 | 16 | 12
|  |  | Assign Role - Permissions to Users to access camera/floor/zone/reports |  | 40 | 24 | 16
0
| 3 | Camera Management | Add/Update/Delete camera |  | 20 | 12 | 8
|  |  | Listing of Cameras with search/filter |  | 16 | 8 | 8
[5 empty] | 0 | 0 | 0
| 4 | Settings | Upload Customer Logo |  | 10 | 6 | 4
|  |  | License Management |  | 20 | 8 | 12
0
| 5 | Site and Zone Management | Add/Update/Delete Site |  | 16 | 8 | 8
|  |  | Add/Update/Delete Floor Plan |  | 20 | 12 | 8
|  |  | Add/Update/Delete Zone on Floor Plan |  | 56 | 40 | 16
|  |  | Add cameras on zones |  | 56 | 32 | 24
|  |  | Camera rotation |  | 36 | 20 | 16
|  |  | Map integration with static map images (The user needs to be online once, maybe while creating the Site, to download the map images, as otherwise, we will not know which country/region/area images to download to make the map work with static map images) |  | 80 | 40 | 40
0
| 6 | Dashboard | Report Filtering |  | 72 | 40 | 32
|  |  | Export to PDF/excel/csv |  | 116 | 76 | 40
0
0
|  |  | Camera - No of Camera Installed |  | 28 | 16 | 12
|  |  | Camera - No of Camera Online/Offline |  | 28 | 16 | 12
|  |  | Camera - Online vs Offline Ratio |  | 28 | 16 | 12
|  |  | Camera - No of Camera by Model Type |  | 28 | 16 | 12
|  |  | Camera - No of Camera by Feature type |  | 28 | 16 | 12
0
|  |  | Site - Total Capacity |  | 20 | 10 | 10
|  |  | Site - Capacity Utilization (%) |  | 20 | 10 | 10
|  |  | Site - Most vs Least Day for Capacity Utilization |  | 20 | 10 | 10
|  |  | Site - Zone wise details for Max Capacity, Utilization, % (Table) |  | 20 | 10 | 10
0
|  |  | People Counting - People In |  | 20 | 10 | 10
|  |  | People Counting - People Out |  | 20 | 10 | 10
|  |  | People Counting - Avg. People In/Out In Day with Min and Max Count |  | 20 | 10 | 10
|  |  | People Counting - Cummulative People Count for Time |  | 20 | 10 | 10
|  |  | People Counting - Zone wise |  | 20 | 10 | 10
|  |  | People Counting - Gender wise |  | 20 | 10 | 10
|  |  | People Counting - People with and without Mask/Helmet |  | 20 | 10 | 10
|  |  | People Counting - Most and Least Count Day for Specific Male and Female |  | 20 | 10 | 10
|  |  | People Counting - Slip and Fall Count for People with Gender |  | 20 | 10 | 10
|  |  | People Counting - New vs Total Visitors |  | 20 | 10 | 10
0
|  |  | Shopping Cart Counting |  | 20 | 10 | 10
|  |  | Heatmap for shopping cart |  | 20 | 10 | 10
|  |  | Queue events for shopping cart |  | 20 | 10 | 10
|  |  | Queue events for people |  | 20 | 10 | 10
|  |  | Blocked exit detection |  | 20 | 10 | 10
0
|  |  | Vehicle - Vehicle Count (Min, Max, Avg. per Day) |  | 20 | 10 | 10
|  |  | Vehicle - Vehicle by Type |  | 20 | 10 | 10
|  |  | Vehicle - Vehicle In/Out |  | 20 | 10 | 10
|  |  | Vehicle - Vehicle in Wrong Direction |  | 20 | 10 | 10
|  |  | Vehicle - Stopped Vehicle Count Time |  | 20 | 10 | 10
|  |  | Vehicle - Speed Detection by Vehicle |  | 20 | 10 | 10
|  |  | Vehicle - Avg. Speed for Vehicle |  | 20 | 10 | 10
|  |  | Vehicle - Traffic Jam by Day |  | 20 | 10 | 10
|  |  | Vehicle - Day wise Traffic (Most and Least) |  | 20 | 10 | 10
|  |  | Vehicle - Speed Violation by Vehicle |  | 20 | 10 | 10
|  |  | Vehicle - Vehicle U Turn detection |  | 20 | 10 | 10
|  |  | Vehicle - Pedestrian detection |  | 20 | 10 | 10
|  |  | Vehicle - Vehicle Turning Movement counts |  | 20 | 10 | 10
|  |  | Vehicle - Vehicle Queue Analysis |  | 20 | 10 | 10
|  |  | Vehicle - Vehicle Detection Heatmap |  | 20 | 10 | 10
0
|  |  | Detect Forklifts |  | 20 | 10 | 10
|  |  | Proximity detection(between people, forklifts, between a person and a forklift) |  | 20 | 10 | 10
|  |  | Forklift speed detection |  | 20 | 10 | 10
|  |  | Counting & Heatmap for forklift and people |  | 20 | 10 | 10
|  |  | Queue events for forklift and people |  | 20 | 10 | 10
|  |  | Blocked exit detection |  | 20 | 10 | 10
0
| 7 | Package creation | R&D on creating a package to install the web application in any windows pc. |  | 0 | 0 | 0
|  |  | Creation of pakage. |  | 0 | 0 | 0
0
| 8 | Data Ingestion | Scheduled calling of Camera APIs to ingest data in database |  | 70 | 0 | 70
0
| 9 | Integration of Camera API | Camera API understanding and Integration |  | 100 | 0 | 100
|  |  | Solar Power and Battery Utilization details will be shown on the dashboard through SNMP/API integration with the BMS and MPTT Controller. ( calling of camera API and just displaying the data available from API) |  | 20 | 10 | 10
0
| 11 | Configuration | Backup and Restore |  | 16 | 0 | 16
0
| 12 | AI Box Integration | AI Box integration, considering addition of multiple cameras in single AI Box and considering the cameras added in the AI Box to display Dashboard widgets data |  | 36 | 16 | 20
0
| 13 | Alexa Integration | Integration with Alexa, so that when the Alexa device is connected, it will open the specific widget on voice command |  | 80 | 40 | 40
0
| 14 | Additional Features added after v2.0 Proposal | Provide data for multiple lanes (8 lanes) |  | 24 | 12 | 12
|  |  | Show heat maps on the floor plans and particular zones |  | 24 | 12 | 12
|  |  | Multisite wise dashboard widget reports |  | 16 | 8 | 8
|  |  | For Multisite there should be filtration to select the widgets and show the difference between, Full site, single zone and Multizone as well |  | 36 | 20 | 16
|  |  | SSL / https set up |  | 16 | 8 | 8
|  |  | Need to have Event reporting details with filtration with separate widgets or separate page for this and when the event reported need to have pre and post video of 5 sec each |  | 70 | 30 | 40
|  |  | Need to have SMTP setup for email reporting. With schedule |  | 32 | 0 | 32
0
|  |  |  | Combined Efforts | 2090 | 990 | 1100
0

## Feature List - Admin Web App
Cost Estimation and Feature Listing for Hanwha Dashboard Web Application - Web App Lead
Development + Unit Testing Efforts
| Sr No | Features/Use Case/WBS | Sub - Features | % Attribution | Combined | Front-end | Back-end
Web Application
| 1 | Admin User Login | Admin user can log in using their own credentials. |  | 16 | 8 | 8
|  |  | User Management |  | 16 | 8 | 8
|  | Customer Management (Separate application) | Customer Details |  | 16 | 8 | 8
|  |  | Customer Licensing details, generating license |  | 100 | 40 | 60
|  |  |  | Combined Efforts | 148 | 64 | 84
0

## Out Of Scope
Sr No. | Out Of Scope
1 | Multilingual support for web application. Application will be only in English language.
2 | Mobile Application Android and iOS native integration

## Weeks Wise Milestones
Sr.No | Milestone Name | No. Of Weeks for the completion
1 | Milestone #2 | 4 Weeks after project kick start
2 | Milestone #3 | 4 Weeks after completion of M #2
3 | Milestone #4 | 6 Weeks after completion of M #3
4 | Milestone #5 | 6 Weeks after completion of M #4